## Planner
Planner
At Risk | Task Name | Start Date | End Date | Assigned To | Duration | % Complete | Comments
TRUE | Planner for all tasks | 2016-02-01 | 2016-02-05 |  | 5d | 20%
| Planner - v1 | 2016-02-01 | 2016-02-02 | Yashwanth | 2d | 100%
| Planner - v2 | 2016-02-03 | 2016-02-04 | Yashwanth | 2d | 50% |  | Weekends
| Final version of Planner | 2016-02-05 | 2016-02-05 | Yashwanth | 1d | 0%
| Review Planner | 2016-02-06 | 2016-02-07 | Both | 1d | 0%
| List down general Topics | 2016-02-01 | 2016-02-05 |  | 5d
| Topics - v1 | 2016-02-01 | 2016-02-02 | Bhavya | 2d
| Topics - v2 | 2016-02-03 | 2016-02-04 | Bhavya | 2d
| Topics - v3 | 2016-02-05 | 2016-02-05 | Bhavya | 1d
| Final version of Topics | 2016-02-06 | 2016-02-07 | Both | 1d
TRUE | Prepare deck for Workshop intiative | 2016-02-08 | 2016-02-26 |  | 15d
| Deck - v1 | 2016-02-08 | 2016-02-13 | Yashwanth | 5d
| Deck - v2 | 2016-02-15 | 2016-02-19 | Yashwanth | 5d
| Deck discussion | 2016-02-20 | 2016-02-21 | Both | 1d
| Changes accordingly | 2016-02-22 | 2016-02-26 | Yashwanth | 5d
| Finalize deck | 2016-02-27 | 2016-02-28 | Yashwanth | 1d
TRUE | Start decks for Workshops | 2016-02-29 | 2016-03-20
WorkShop deck - v1
WorkShop deck - v2
WorkShop deck - v3
WorkShop deck - v4
WorkShop deck - v5
Finalize Workshop deck
Formulas:
End Date = [Start Date]+4
End Date = [End Date, row above]+2
Start Date = [Start Date, row above]
Start Date = [Start Date, row above]+2

## Gantt Chart
Gantt Chart

## Discussions
Discussion Forum
Discussion Title | Summary | Comments/Suggestions | Lessons | Remarks
Name the discussion | Brief the discussion | Add Suggestions | What we learn? | How good discussion went?