## Project Plan
Action Plan
Understanding of Business Problem
1. Determine the Customer behaviour & identify which set of customers contributing to maximum share of the Margin. This helps the business to idenfity which customers to target. Also determining the item-lists of Profitable customers provides support to merchants to what items to carry.
2. Suppose a new customer carries better sales volume, examine how long customer continue to stay with Kobalt. This supports the business to function with better customer retention policies.
3. Distinguish the Non-Kobalt customers versus Kobalt customers & determine the customers hereafter who persuades as Kobalt(potential) customers. This will reinforces the business through the expansion of customer database.
Methodology to be used
1. Analyze customer d/b rolling 52-weeks by determing the customer group who are driving 80% of margin & also enlist the corresponding item-sets. Hereafter called as Profitable customers.
2. Merge the demography, dwelling & income factors of profitable customers. Classify these customers in order to understand their practice of buying items.
3. Validate through precision matrix to proceed ahead with an appropriate classification technique.
4. Predict the probability of each customer remains as profitable customer to Kobalt
5. Randomly pick the Non-Kobalt customers & draw a sales pattern against Kobalt profitable customers. If trends are of same direction, then those customers are assumed to be potential customers. Validate through classification(binary). Demography, dwelling & income factors are added further classification analysis.
Timeline for each steps to be executed Due Dates
Scope 30-Nov 2016
Analyze 07-Dec 2016
Merge 07-Dec 2016
Classification 07-Dec 2016
Validation & Prediction 08-Dec 2016
Classification(Kobalt v/s Non-Kobalt) 09-Dec 2016
Insights delivery 09-Dec 2016
Review-1 09-Dec 2016
Review-2 12-Dec 2016
Final Presentation 13-Dec 2016

## Planner (hidden)
Objective: Kobalt is a private label brand and the business wants to understand the Kobalt customers better. It is also important to understand if those customers are profitable. Also we need to find out the potential customers whose probability of shopping in Kobalt is high. This will give the business a good understanding of potential business opportunity.
Scope:
Kobalt Customers | 1. Identify the customers who has 80% of the profits(margin %) from 20% customer base(80-20 rule). Loyalty customers who proactively purchases items(small) & visits the stores frequently.
2. What are most profitable customers buying & which products are more often purchased?
3. What demographical, dwelling & Income group factors comprises profitable customers?
4. Examine sales volume of new customers & demistify their behaviour, hereafter who resides as Kobalt customers
Non-Kobalt Customers | 1. Determine the Sales pattern(& Income group) of Non-Kobalt customers versus Kobalt customers for the course of analysis period. Classify the Non-Kobalt customers through behaviours comprises of Sales, Geograhical locations, transactions, purchase order value to segment potential customers.
Action Plan Timeline(Ball Park)
Phase 1 - Methodolgy framing and data read to be completed 01-Dec
a.Optimize item list & analyze customer d/b rolling 52-weeks 29-Nov
b. Gather the required data & check every inputs are in place 29-Nov
c. Perform EDA & understand the behaviour of performance metrics 01-Dec
Phase 2 - Analysis & Insigths to be delivered 06-Dec
a. Idenfity the clusters(groups) of profitable customers to offer recommendations 02-Dec
b. Predict the outcome(probablilty) of potential customers shopping for Kobalt 04-Dec
c. Validate(Confusion matrix) the customer list through different classification techniques 05-Dec
d. Get final customer list reviewed by core team & present it on final day 06-Dec
Phase 3 - Final presentation 08-Dec
Analysis Period
From : Week 2015-11-06
To : Week 2016-10-28